## Sheet1
编号 | 问题 | 解决效果 | 状态 | 负责人
16197 | WEB - Indication of the routing disappears when user unchecks the checkbox of the some output. | 显示切换状态
16223 | WEB - VGAA IN - Routing settings - click on the active port - The 'save' button is not necessary because the user can not change nothing | 无参数修改的状态下，SAVE按钮不可用
16238 | WEB - Routing settings - When web page is reloaded the check box "ALL" is recognized as not selected ,although the user selected the check box. | 切换界面应该记住设置的状态
16104 | WEB - Copy EDID to the inactive port (card is missing inthe slot)- The copy process seems like in endless loop | 拷贝EDID出现类似死机的情况
16258 | WEB - EDID error message appears without some reason
15717 |  | 负载EDID变化修改EDID的信息
16105 | WEB - After saving a change on the Settings page , the page refreshes to the Routing page | 设置界面修改参数，不需要跳转至切换界面
16177 | WEB - The following message displays - "Save success",when GATE " and "IP" defined identically. | 显示错误的网络配置信息，IP地址改变重加载
16143 | WEB - "Start upgrade" button should be disabled after the first pressing on the button and "waiting" process should be displayed. | 升级过程中不可操作的按钮不可用 |  | 贾
16148 | WEB - There is unnecessary and not clear message when user changes the device settings | 修改网络参数验证，清除不必要的信息
16152 | WEB - Upgrade the card - The progress bar always displays 25% and in the end of the process the web page returns to the "device" and not to the "card" web page. | 显示升级进度
16153 | WEB - Upgrade the card - Not clear message appears as "rename error",when user try to upgrade the empty slot. | 选择不存在的设备升级状态显示为灰色不可执行
16160 | WEB - VGAA-IN8-F64 - there is not clear message appears, when user set illegal value. | 非法输入校验
16247 | WEB - VGAA-OUT8-F64 - there is not clear message appears ,when user set illegal value. | 非法参数校验
16248 | WEB-DTAXR-In4-F32- Empty Prompt message appears when saving a value other than numbers. | 非法输入校验
16249 | WEB-DTAXR-Out4-F32- Empty Prompt message appears when saving a value other than numbers. | 非法数据校验
16260 | WEB-VGAA-In4-F32- Empty Prompt message appears when saving a value other than numbers. | 非法输入校验
16162 | WEB - "Save changes" button should be disabled after the first pressing on the button and waiting process should be dispalyed - several pressing on the buton cause to the networking error. | 设置按钮应当等待可执行时显示有效
16168 | WEB - "Repower" and "Factory " buttons should be disabled after the first pressing,the "waiting" process should be displayed. | 复位或者是重启按钮按下后将进入不可用状态
16246 | WEB - VGAA-OUT8-F64 - There is not correct message appears - "Save success",although the value was not saved | 非法输入校验
16204 |  | 更新Kramer新的网址 |  | 贾